## Sheet1
	May 2021	June 2021	July 2021	August 2021	September 2021	October 2021	November 2021	December 2021	January 2022	February 2022	March 2022	April 2022	May 2022	June 2022	July 2022	August 2022	September 2022		Size of task
Attend MIC 2021
MIC 2022 submission																			Small
Write thesis																			Medium
Edit thesis																			Large
MSc supervision
Harvard image derived input function collaboration
Dynamic surrogate signal extraction parameter search
Implement volume based surrogate signal evaluation
Evaluation of neural network based surrogate signal selection method
Write dynamic surrogate signal extraction paper
NAC motion correction parameter search
Post reconstruction NAC motion correction evaluation
Pilot study into motion correction with patient data
Investigation into stochastic motion modelling methods
Investigation into robust motion modelling methods
AC motion correction parameter search
Post reconstruction AC motion correction evaluation
Iterative motion correction evaluation
Full study into motion correction with patient data
Write image space motion correction paper
Implement sinogram space registration
Implement sinogram space simple motion model
Post reconstruction sinogram space simple motion model evaluation
Iterative sinogram space simple motion model evaluation
Implement sinogram space complex motion model
Post reconstruction sinogram space complex motion model evaluation
Iterative sinogram space complex motion model evaluation
Write sinogram space motion correction paper